## README
ClaimSense — Project Tracker
Health-insurance claim adjudication · Agentic AI Capstone · Team of 6
WHAT EACH TAB IS FOR
Dashboard | Live progress: per member, per phase, per lecture layer. All formulas — do not type here.
Analysis | High-level analysis: scope, critical path, workload balance, risks.
Team | Fill in member names, emails, backups. Names flow into every other tab.
Master Tasks | Single source of truth: every task with Problem, Date, Status, Owner. Pre-filled with 64 tasks from the capstone brief.
1-Domain … 6-DevOps | One tab per person: their daily update log (Date, what I did, plan, problem, help needed, hours, evidence).
Problems Log | Every problem/blocker with date raised, owner, days open and resolution. Pre-filled with the open questions from the Discord playbook.
Handoffs | The 9 cross-role handoffs from the playbook, with due dates and status.
Decisions (ADR) | Index of architecture decisions.
Experiments | E1–E4 results in the format the brief requires.
LEGEND
Yellow cells | Input cells — fill these in.
Dropdowns | Status, Owner, Priority, Layer use dropdown lists. Pick from the list so the Dashboard counts correctly.
Status values | Not Started → In Progress → In Review → Done, or Blocked.
TEAM RULES FOR THIS SHEET
Daily | Add one row to your own tab by 10:00 on workdays (same as the #daily-updates rule).
When a task moves | Update Status and % Done in Master Tasks. If blocked, set Blocked, fill Problem + Problem Date, and add a row in Problems Log.
Evidence | Always paste a GitHub issue/PR/doc link. GitHub stays the source of truth; this sheet is the progress view.
Friday | 15-minute review of the Dashboard: overdue tasks, open problems, members with no updates.
Never | No API keys, real claim data or patient details in this sheet.
EXAMPLE ROWS (format to follow)
Daily log row | 2026-10-28 ¦ T09 ¦ Parsed policy PDF into 112 clauses ¦ Add clause metadata + tests ¦ PDF tables break chunking ¦ Open ¦ Tools & Security ¦ 4 ¦ github.com/…/pull/7
Problems Log row | PB-07 ¦ 2026-11-04 ¦ Agents & Orchestration ¦ T26 ¦ L11 Multi-agent ¦ Coverage agent cites wrong clause for ICU ¦ High ¦ Knowledge & Memory ¦ Open ¦ ¦ (auto) ¦ ¦ issue #21
ASSUMPTIONS
Dates | Phase dates assume a ~9-week plan from 26 Oct 2026 to a final review in the week of 21 Dec 2026. The brief does not give the review date — edit the Phase table on the Dashboard and the Due Dates once it is known.
Owners | Task owners follow the six roles in the capstone guide. Reassign any task with the Owner dropdown.

## Dashboard
ClaimSense — Progress Dashboard
All cells are formulas. Update Master Tasks, member tabs and Problems Log; this page updates itself.
Today
Total tasks
Done
% Done
In progress / review
Blocked
Overdue
Open problems
Avg % complete (all tasks)
PROGRESS BY MEMBER
Role | Member | Tasks | Done | In Progress / Review | Blocked | Overdue | % Done | Avg % Complete | Open Problems | Hours Logged | Last Log Update | Days Since Update
Domain & Product Lead
Knowledge & Memory
Agents & Orchestration
Tools & Security
Eval & Red-Team
Deploy & Ops
All (team tasks) | Whole team
PROGRESS BY PHASE
Phase | Start | End | Tasks | Done | % Done | Phase Status
P0 Setup & Planning | 2026-10-26 | 2026-10-30
P1 Foundations | 2026-11-02 | 2026-11-13
P2 Minimum Bar End-to-End | 2026-11-16 | 2026-11-27
P3 Signature Challenges + Eval | 2026-11-30 | 2026-12-11
P4 Experiments & Report | 2026-12-14 | 2026-12-18
P5 Demo & Submission | 2026-12-21 | 2026-12-24
MINIMUM-BAR COVERAGE BY LECTURE LAYER
Layer | Tasks | Done | % Done | Blocked
Project Mgmt
Domain/Product
L4–L6 Retrieval
L7 Tools/MCP
L8 Orchestration
L9 Memory
L10 Planning
L11 Multi-agent
L12 Improvement
L13 Evaluation
L14 Human control
L15 Security
L16 Deployment
Formulas:
Days Since Update = IF(ISNUMBER([Last Log Update]),TODAY()-[Last Log Update],"—")
Overdue = IF([Done]=0,"—",IF([In Progress / Review]=[Done],"Complete",IF(TODAY()<[Member],"Upcoming",IF(TODAY()>[Tasks],"Behind","Active"))))
Note on B26: Assumed dates — edit when the final review date is confirmed.

## Analysis
ClaimSense — High-Level Analysis
Built from the capstone guide (16 Oct 2026) and the team Discord playbook (25 Oct 2026).
1. PROJECT IN BRIEF
Goal | Read a hospitalisation claim, check every bill line against the Arogya Sanjeevani policy wording, compute rupee amounts in code, and prepare a settlement for a claims adjudicator to approve.
User | Claims adjudicator at an insurer or TPA. Today the work is slow, inconsistent, and padded bills are common.
Signature A | Money you can audit — every rupee from unit-tested code, every deduction cites a clause; proportional cut after a room-rent breach done correctly. Owners: Tools & Security (calculator), Agents (coverage analyst).
Signature B | Playbook that learns from adjudicator edits — Reflexion loop on dev claims, human-approved lessons, frozen before held-out run. Owners: Agents (loop), Knowledge (lesson store), Eval (E3).
Marks | Roughly equal: scope & impact · technical depth · presentation · individual viva. Every member must redraw the architecture from memory.
Demo (3 scenes) | (1) Room-rent proportional cut explained line by line. (2) Injected 'pre-approved' note ignored + duplicate bill caught. (3) Edit one line → totals recalc → old approval invalid.
2. WORKLOAD BALANCE (live from Master Tasks)
Role | Tasks | Critical | High | Share of All Tasks | Comment
Domain & Product Lead |  |  |  |  | Light on code — owns domain content: wording, tariff, synthetic claims, demo, slides.
Knowledge & Memory |  |  |  |  | Front-loaded: retrieval must be ready by mid-Nov for agents.
Agents & Orchestration |  |  |  |  | Heaviest build load and on the critical path; backup should review every PR.
Tools & Security |  |  |  |  | Calculator (Signature A) is the single most important piece of code — start Week 2.
Eval & Red-Team |  |  |  |  | Heaviest in Weeks 6–8 (80 hand worksheets + E1–E4 + report). Start the golden set early.
Deploy & Ops |  |  |  |  | Steady load; Docker + tracing early unblocks everyone.
All |  |  |  |  | Shared tasks: setup, E2E run, contribution review, viva prep.
3. CRITICAL PATH (if any of these slip, the demo slips)
Step 1 | T06 Policy wording verified → T09 Ingestion → T10 Hybrid index → T16 policy-kb server
Step 2 | T15 Adjudication calculator (parallel, from Week 2) → T26 Coverage analyst
Step 3 | T23 LangGraph graph + T34 Approval gate → T38 First end-to-end run (target 27 Nov)
Step 4 | T22 Golden-set spec → T39 80 expected worksheets → T41 Eval harness → T51–T54 Experiments → T57 Report
Step 5 | T45 Reflexion loop needs a working E2E pipeline AND the harness — it cannot start before ~30 Nov
4. TOP RISKS
Risk | Likelihood | Impact | Owner | Mitigation | Status
Proportional cut after room-rent breach implemented wrong | Medium | High | Tools & Security | Hand-worked examples from the wording as unit tests before any agent uses the calculator. | Open
80 hand-made worksheets take far longer than planned | High | High | Eval & Red-Team | Start in P1; Domain Lead drafts cases, Eval computes; spreadsheet template per claim. | Open
Held-out leakage (tuner writes or sees held-out cases) | Medium | High | Eval & Red-Team | Separate folder the agent can't read; Agents role never writes held-out cases; Domain checks them. | Open
Late integration — components don't fit together | Medium | High | Deploy & Ops | Docker Compose + interface handoffs agreed by 13 Nov; E2E run on 27 Nov is a hard milestone. | Open
Ambiguous ownership of L13/L15 | High | Medium | Eval & Red-Team | Close PB-01/PB-02 with ADR-0002 this week. | Open
Health data / keys leak into traces, Discord or this sheet | Low | High | Tools & Security | Synthetic data only; masking in hooks; secret scanning; AutoMod rule. | Open
LLM cost/rate limits during repeated eval runs | Medium | Medium | Deploy & Ops | Cache, fixed small model for specialists, cost per case on dashboard. | Open
Final review date unknown — plan may be too long/short | Medium | Medium | Domain & Product Lead | Confirm date (PB-07) and re-date phases on the Dashboard. | Open
5. RULES THAT PROTECT THE MARKS
Model proposes, code decides | Arithmetic, eligibility, money and permissions live in tested code. The model picks the clause and explains.
Outside text is data | Discharge summaries, bills and retrieved passages may contain injected instructions.
Exact-payload approval | Approval is tied to the worksheet hash; any edit invalidates it. Two levels above the threshold.
Two separations | Whoever tunes the agent does not write held-out cases; whoever builds defences does not write attacks. Eval & Red-Team owns both.

## Team
Team & Roles
Fill in the yellow cells. Member names appear automatically on every other tab.
Role | Member Name | Backup | Email | Layers | Main Deliverables | GitHub Label | Log Tab
Domain & Product Lead | Member 1 |  |  | — | Problem statement, persona, policy wording, tariff table, synthetic claims, held-out check, demo script | area:domain | 1-Domain
Knowledge & Memory | Member 2 |  |  | L4–L6, L9 | Ingestion, hybrid retrieval + reranker, claim-history memory, lesson store, memory policy | area:knowledge | 2-Knowledge
Agents & Orchestration | Member 3 |  |  | L8, L10–L12 | LangGraph graph, planner, 5 specialist agents, critic loop, Reflexion playbook | area:agents | 3-Agents
Tools & Security | Member 4 |  |  | L7, L14, L15 | 4 MCP servers, adjudication calculator, hooks, approval gate, guardrails, threat model | area:tools-security | 4-ToolsSec
Eval & Red-Team | Member 5 |  |  | L13 harness, L15 evals | Golden set (80 claims), harness, judge calibration, red-team suite, E1–E4, eval report | area:eval | 5-Eval
Deploy & Ops | Member 6 |  |  | L13 CI gate, L16 | FastAPI + UI, Docker Compose, CI eval gate, tracing, Grafana, alerts | area:ops | 6-DevOps
Key links
GitHub repo
Projects board
Discord server
Google Drive folder
Final review date

## Master Tasks
ID | Phase | Layer | Task | Deliverable / Evidence | Owner (Role) | Member | Start Date | Due Date | Status | % Done | Priority | Depends On | Problem / Blocker | Problem Date | Resolution | Evidence Link | Overdue? | Notes
T01 | P0 Setup & Planning | Project Mgmt | Assign the 6 roles and backups; fill in the Team tab | Team tab complete | All |  | 2026-10-26 | 2026-10-30 | Not Started | 0% | High
T02 | P0 Setup & Planning | Project Mgmt | Create GitHub repo, Projects board, area labels, milestones | Repo + board link in Team tab | Deploy & Ops |  | 2026-10-26 | 2026-10-30 | Not Started | 0% | High
T03 | P0 Setup & Planning | Project Mgmt | Set up the Discord server per the playbook | Server live, checklist ticked | Deploy & Ops |  | 2026-10-26 | 2026-10-30 | Not Started | 0% | Medium
T04 | P0 Setup & Planning | Project Mgmt | Each role writes a one-page plan for its layers | 6 plans linked from issues | All |  | 2026-10-26 | 2026-10-30 | Not Started | 0% | High | T01
T05 | P0 Setup & Planning | L13 Evaluation | ADR: L13/L15 ownership split (Eval vs Deploy, threat-model sign-off) | ADR-0002 accepted | Eval & Red-Team |  | 2026-10-26 | 2026-10-30 | Not Started | 0% | High
T06 | P0 Setup & Planning | Domain/Product | Download Arogya Sanjeevani wording (1–2 insurers); verify CIS numbers (room 2%/₹5k, ICU 5%/₹10k, cataract, 5% co-pay, waiting periods) | Wording PDFs + verified rules sheet | Domain & Product Lead |  | 2026-10-26 | 2026-10-30 | Not Started | 0% | High
T07 | P0 Setup & Planning | Domain/Product | Write problem statement and claims-adjudicator persona | docs/problem.md | Domain & Product Lead |  | 2026-10-26 | 2026-10-30 | Not Started | 0% | Medium
T08 | P0 Setup & Planning | Project Mgmt | Open handoff issues from the Handoffs tab with agreed format + date | 9 handoff issues | All |  | 2026-10-26 | 2026-10-30 | Not Started | 0% | High | T04
T09 | P1 Foundations | L4–L6 Retrieval | Ingestion: policy PDF → one chunk per numbered clause, keep clause no., insurer, date | Ingestion script + chunk sample | Knowledge & Memory |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High | T06
T10 | P1 Foundations | L4–L6 Retrieval | Hybrid index: BM25 + vectors with RRF, cross-encoder reranker | Index + retrieval API | Knowledge & Memory |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High | T09
T11 | P1 Foundations | L4–L6 Retrieval | Query rewrite of bill-line terms (e.g. 'OT charges') into policy language | Rewrite module + examples | Knowledge & Memory |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | Medium | T10
T12 | P1 Foundations | L4–L6 Retrieval | Label 30+ retrieval queries; measure Recall@5 baseline | Recall@5 baseline number | Knowledge & Memory |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High | T10
T13 | P1 Foundations | Domain/Product | Build tariff table: 30 procedures × 3 city tiers | tariff.csv | Domain & Product Lead |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High
T14 | P1 Foundations | Domain/Product | Synthetic claim packet generator + 10 hand-edited packets (no real patient data) | Packets in data/synthetic | Domain & Product Lead |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High | T06
T15 | P1 Foundations | L7 Tools/MCP | adjudication-calc: room cap, proportional cut, sub-limits, co-pay in plain Python + unit tests | Calculator with passing tests (Signature A) | Tools & Security |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | Critical | T06
T16 | P1 Foundations | L7 Tools/MCP | policy-kb MCP server (search wording, get clause) | Tool schema + 1 test | Tools & Security |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High | T10
T17 | P1 Foundations | L7 Tools/MCP | tariff MCP server (expected range per procedure + tier) | Tool schema + 1 test | Tools & Security |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | Medium | T13
T18 | P1 Foundations | L7 Tools/MCP | claims-db MCP server + schema (history read; settle_claim write behind gate) | Tool schema + 1 test | Tools & Security |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High
T19 | P1 Foundations | L16 Deployment | Docker Compose skeleton: app, MCP servers, vector store, Prometheus, Grafana | docker compose up works | Deploy & Ops |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High
T20 | P1 Foundations | L16 Deployment | One versioned config for prompts and model IDs | config/ file | Deploy & Ops |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | Medium
T21 | P1 Foundations | L13 Evaluation | Tracing (Langfuse/LangSmith) with health data masked | Trace screenshot (masked) | Deploy & Ops |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | Medium | T19
T22 | P1 Foundations | L13 Evaluation | Golden-set spec: 80 claims, case mix, ~20 dev / 60 held-out split | Golden-set plan doc | Eval & Red-Team |  | 2026-11-02 | 2026-11-13 | Not Started | 0% | High
T23 | P2 Minimum Bar End-to-End | L8 Orchestration | LangGraph graph: typed state, conditional edges, persistent checkpointer; stop + resume | Graph diagram + resume demo | Agents & Orchestration |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | Critical
T24 | P2 Minimum Bar End-to-End | L10 Planning | Planner: show plan object; replan when a tool result contradicts it | Trace showing a replan | Agents & Orchestration |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High | T23
T25 | P2 Minimum Bar End-to-End | L11 Multi-agent | Extraction agent: typed fields + every bill line with source spans | Extraction output on 10 packets | Agents & Orchestration |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High | T14
T26 | P2 Minimum Bar End-to-End | L11 Multi-agent | Coverage analyst: clause per line, calls calculator (model picks clause, code computes ₹) | Worksheet output | Agents & Orchestration |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | Critical | T15,T16
T27 | P2 Minimum Bar End-to-End | L11 Multi-agent | Fraud analyst: duplicates, tariff outliers, date checks | Fraud flags on test packets | Agents & Orchestration |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | Medium | T17,T18
T28 | P2 Minimum Bar End-to-End | L11 Multi-agent | Critic agent + one-revision loop (re-run calc, check citations) | Critic rejection trace | Agents & Orchestration |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High | T26
T29 | P2 Minimum Bar End-to-End | L11 Multi-agent | Settlement agent + letter with reason per deduction | Sample letter | Agents & Orchestration |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | Medium | T34
T30 | P2 Minimum Bar End-to-End | L11 Multi-agent | Single-agent baseline with same tools and budget | Baseline runnable | Agents & Orchestration |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High | T26
T31 | P2 Minimum Bar End-to-End | L9 Memory | Claim history per policy (sub-limits used, bills seen) + memory policy page | Memory policy (1 page) | Knowledge & Memory |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High | T18
T32 | P2 Minimum Bar End-to-End | L9 Memory | Short-term context trimming/summarising | Config + test | Knowledge & Memory |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | Medium | T23
T33 | P2 Minimum Bar End-to-End | L14 Human control | Hooks: pre-tool permission + budget; post-tool log + scrub | Hook tests | Tools & Security |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High
T34 | P2 Minimum Bar End-to-End | L14 Human control | Approval gate: interrupt() tied to worksheet hash; 2 levels above threshold | Edit-invalidates-approval demo | Tools & Security |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | Critical | T23
T35 | P2 Minimum Bar End-to-End | L15 Security | Input guardrails: mask health data, injection check, documents as data | Guardrail tests | Tools & Security |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High
T36 | P2 Minimum Bar End-to-End | L15 Security | Output guardrails: deductions cited, totals add up, right patient/policy no. | Guardrail tests | Tools & Security |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High
T37 | P2 Minimum Bar End-to-End | L16 Deployment | FastAPI with streaming + case UI (upload packet, view worksheet, approve/edit) | UI demo | Deploy & Ops |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | High | T19
T38 | P2 Minimum Bar End-to-End | Project Mgmt | First end-to-end run on 5 dev claims | E2E trace | All |  | 2026-11-16 | 2026-11-27 | Not Started | 0% | Critical | T23,T37
T39 | P3 Signature Challenges + Eval | L13 Evaluation | Hand-calculate expected worksheets for 80 claims (room-rent breach, waiting period, duplicates, consumables, partial sub-limits, out-of-period) | Expected worksheets | Eval & Red-Team |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | Critical | T22
T40 | P3 Signature Challenges + Eval | Domain/Product | Check held-out cases against written policy | Sign-off note | Domain & Product Lead |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | High | T39
T41 | P3 Signature Challenges + Eval | L13 Evaluation | Eval harness: pytest/JSONL runner, code checkers (amounts, citations, DB state, tool calls) | Harness CLI | Eval & Red-Team |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | Critical | T38
T42 | P3 Signature Challenges + Eval | L13 Evaluation | LLM judge (different family) vs 20+ human labels; Cohen's kappa | Kappa value | Eval & Red-Team |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | High | T41
T43 | P3 Signature Challenges + Eval | L15 Security | One-page threat model | docs/threat-model (private) | Tools & Security |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | High
T44 | P3 Signature Challenges + Eval | L15 Security | Red-team suite 30+ attacks: 'pre-approved' note, bill total ≠ sum, altered date, wrong patient | Attack suite | Eval & Red-Team |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | High | T43
T45 | P3 Signature Challenges + Eval | L12 Improvement | Reflexion loop on dev claims: adjudicator edits → lessons; human review; freeze (Signature B) | Playbook + 1 rejected lesson | Agents & Orchestration |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | Critical | T41
T46 | P3 Signature Challenges + Eval | L9 Memory | Lesson store: retrieve only relevant lessons; withdraw a lesson | Lesson retrieval test | Knowledge & Memory |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | High | T45
T47 | P3 Signature Challenges + Eval | L7 Tools/MCP | Proportional-cut audit: line-by-line explanation of the calculation | Explainer output (Signature A) | Tools & Security |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | High | T15
T48 | P3 Signature Challenges + Eval | L16 Deployment | CI with eval gate that fails below threshold | Failing CI run explained | Deploy & Ops |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | High | T41
T49 | P3 Signature Challenges + Eval | L16 Deployment | Grafana: claims processed, edit rate, ₹ deducted by reason, fraud flags, turnaround, cost/claim | Dashboard screenshot | Deploy & Ops |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | High | T21
T50 | P3 Signature Challenges + Eval | L16 Deployment | Alert when adjudicator edit rate rises | Alert fired once | Deploy & Ops |  | 2026-11-30 | 2026-12-11 | Not Started | 0% | Medium | T49
T51 | P4 Experiments & Report | L13 Evaluation | E1: C0 fixed workflow vs C1 single agent vs C2 team | E1 results | Eval & Red-Team |  | 2026-12-14 | 2026-12-18 | Not Started | 0% | High | T30,T41
T52 | P4 Experiments & Report | L15 Security | E2: defences off vs on (attack success + false blocks) | E2 results | Eval & Red-Team |  | 2026-12-14 | 2026-12-18 | Not Started | 0% | High | T44
T53 | P4 Experiments & Report | L12 Improvement | E3: held-out before vs after playbook, 3 repeats, lesson cost | E3 results | Eval & Red-Team |  | 2026-12-14 | 2026-12-18 | Not Started | 0% | High | T45
T54 | P4 Experiments & Report | L13 Evaluation | E4: LLM arithmetic vs calculator — rupee error | E4 results | Eval & Red-Team |  | 2026-12-14 | 2026-12-18 | Not Started | 0% | High | T15
T55 | P4 Experiments & Report | L9 Memory | Memory on vs off comparison | Comparison table | Knowledge & Memory |  | 2026-12-14 | 2026-12-18 | Not Started | 0% | Medium | T31
T56 | P4 Experiments & Report | L4–L6 Retrieval | Recall@5 before vs after one change | Before/after numbers | Knowledge & Memory |  | 2026-12-14 | 2026-12-18 | Not Started | 0% | Medium | T12
T57 | P4 Experiments & Report | L13 Evaluation | Evaluation report (4–6 pages) | Report PDF | Eval & Red-Team |  | 2026-12-14 | 2026-12-18 | Not Started | 0% | Critical | T51,T52,T53,T54
T58 | P4 Experiments & Report | L16 Deployment | Clean-machine install test; README one-command start | Install log | Deploy & Ops |  | 2026-12-14 | 2026-12-18 | Not Started | 0% | High
T59 | P5 Demo & Submission | Domain/Product | Demo script (3 scenes) + 2 rehearsals | Script + rehearsal notes | Domain & Product Lead |  | 2026-12-21 | 2026-12-24 | Not Started | 0% | Critical
T60 | P5 Demo & Submission | Project Mgmt | Redrawn architecture diagram + numbered walkthrough | Diagram in docs/ | Agents & Orchestration |  | 2026-12-21 | 2026-12-24 | Not Started | 0% | High
T61 | P5 Demo & Submission | Domain/Product | Slides | Slide deck | Domain & Product Lead |  | 2026-12-21 | 2026-12-24 | Not Started | 0% | High | T57
T62 | P5 Demo & Submission | L16 Deployment | Backup demo recording | Video file | Deploy & Ops |  | 2026-12-21 | 2026-12-24 | Not Started | 0% | High | T59
T63 | P5 Demo & Submission | Project Mgmt | Final contribution-log review | CONTRIBUTIONS.md | All |  | 2026-12-21 | 2026-12-24 | Not Started | 0% | High
T64 | P5 Demo & Submission | Project Mgmt | Viva prep: everyone redraws the architecture and explains their part | Mock viva done | All |  | 2026-12-21 | 2026-12-24 | Not Started | 0% | High | T60
Formulas:
Overdue? = IF(OR([Due Date]="",[Status]="Done"),"",IF([Due Date]<TODAY(),"OVERDUE",""))
Note on B1: Phase dates are an assumption (see README). Edit Start/Due dates per task as needed.
Note on K1: Enter as a percentage, e.g. 50%. Set 100% when Status = Done.

## 1-Domain
Layers: — · Problem statement, persona, policy wording, tariff table, synthetic claims, held-out check, demo script
Updates logged: |  | Open problems: |  | Hours logged: |  | My open tasks:
Date | Task ID | What I Did | Plan Next | Problem / Blocker | Problem Status | Help Needed From | Hours | Evidence Link (PR / Issue / Doc) | Handoff Others Are Waiting On

## 2-Knowledge
Layers: L4–L6, L9 · Ingestion, hybrid retrieval + reranker, claim-history memory, lesson store, memory policy
Updates logged: |  | Open problems: |  | Hours logged: |  | My open tasks:
Date | Task ID | What I Did | Plan Next | Problem / Blocker | Problem Status | Help Needed From | Hours | Evidence Link (PR / Issue / Doc) | Handoff Others Are Waiting On

## 3-Agents
Layers: L8, L10–L12 · LangGraph graph, planner, 5 specialist agents, critic loop, Reflexion playbook
Updates logged: |  | Open problems: |  | Hours logged: |  | My open tasks:
Date | Task ID | What I Did | Plan Next | Problem / Blocker | Problem Status | Help Needed From | Hours | Evidence Link (PR / Issue / Doc) | Handoff Others Are Waiting On

## 4-ToolsSec
Layers: L7, L14, L15 · 4 MCP servers, adjudication calculator, hooks, approval gate, guardrails, threat model
Updates logged: |  | Open problems: |  | Hours logged: |  | My open tasks:
Date | Task ID | What I Did | Plan Next | Problem / Blocker | Problem Status | Help Needed From | Hours | Evidence Link (PR / Issue / Doc) | Handoff Others Are Waiting On

## 5-Eval
Layers: L13 harness, L15 evals · Golden set (80 claims), harness, judge calibration, red-team suite, E1–E4, eval report
Updates logged: |  | Open problems: |  | Hours logged: |  | My open tasks:
Date | Task ID | What I Did | Plan Next | Problem / Blocker | Problem Status | Help Needed From | Hours | Evidence Link (PR / Issue / Doc) | Handoff Others Are Waiting On

## 6-DevOps
Layers: L13 CI gate, L16 · FastAPI + UI, Docker Compose, CI eval gate, tracing, Grafana, alerts
Updates logged: |  | Open problems: |  | Hours logged: |  | My open tasks:
Date | Task ID | What I Did | Plan Next | Problem / Blocker | Problem Status | Help Needed From | Hours | Evidence Link (PR / Issue / Doc) | Handoff Others Are Waiting On

## Problems Log
ID | Date Raised | Raised By | Task ID | Layer | Problem | Impact | Assigned To | Status | Date Resolved | Days Open | Resolution | Link
PB-01 | 2026-10-25 | Domain & Product Lead | T05 | L13 Evaluation | L13 is listed under two roles. Confirm split: Eval owns harness + metrics, Deploy owns CI gate + dashboards. | High | Eval & Red-Team | Open
PB-02 | 2026-10-25 | Domain & Product Lead | T05 | L15 Security | L15 is shared between Tools/Security (guardrails) and Eval (security evals). Who signs off the threat model? | High | Tools & Security | Open
PB-03 | 2026-10-25 | Domain & Product Lead |  | Project Mgmt | Who are the mentors and the domain expert, and how often will they join? | Medium | Domain & Product Lead | Open
PB-04 | 2026-10-25 | Domain & Product Lead |  | Project Mgmt | Do the brief or university require data-handling / privacy rules for Discord and shared docs? | Medium | Domain & Product Lead | Open
PB-05 | 2026-10-25 | Domain & Product Lead | T64 | Project Mgmt | Are grades based on individual contribution evidence? What format does the course expect? | High | Domain & Product Lead | Open
PB-06 | 2026-10-25 | Domain & Product Lead |  | Project Mgmt | Which tools beyond GitHub are approved (Google Drive/Sheets, Notion, Excalidraw)? | Low | Domain & Product Lead | Open
PB-07 | 2026-10-25 | Domain & Product Lead |  | Project Mgmt | Final review / demo date not in the brief — needed to fix the phase plan. | High | Domain & Product Lead | Open
Formulas:
Days Open = IF([Date Raised]="","",IF([Date Resolved]="",TODAY()-[Date Raised],[Date Resolved]-[Date Raised]))
Note on K1: Red when open for more than 2 days — the playbook escalates to a mentor after 48 h.

## Handoffs
# | From | To | What Is Handed Over | Needed Before | Due Date | Status | GitHub Issue | Notes
1 | Domain & Product Lead | Knowledge & Memory | Policy documents and source corpus, with permitted-use notes | Ingestion work starts | 2026-11-02 | Not Started
2 | Domain & Product Lead | Eval & Red-Team | Golden-set cases and expected answers | The first eval run | 2026-11-27 | Not Started
3 | Knowledge & Memory | Agents & Orchestration | Retrieval and memory interface (signatures, return format) | Specialist agents call retrieval | 2026-11-13 | Not Started
4 | Tools & Security | Agents & Orchestration | MCP tool contracts, approval-gate hooks, guardrail API | Agents use tools | 2026-11-13 | Not Started
5 | Agents & Orchestration | Eval & Red-Team | Runnable graph entry point and trace output | End-to-end evals | 2026-11-27 | Not Started
6 | Eval & Red-Team | Deploy & Ops | Eval CLI, metrics and pass thresholds | The CI eval gate | 2026-12-04 | Not Started
7 | Eval & Red-Team | Tools & Security | Red-team findings (via #security-private) | Each guardrail iteration | 2026-12-11 | Not Started
8 | Deploy & Ops | All | Docker Compose dev environment, tracing setup | Week 2 integration | 2026-11-06 | Not Started
9 | All | Domain & Product Lead | Demo-ready features and known limitations | Demo rehearsal | 2026-12-18 | Not Started
Note on F1: Proposed dates aligned to the phase plan (assumption). Agree the real date in the handoff issue.

## Decisions (ADR)
ADR # | Date | Title | Owner | Layers | Status | Link (docs/adr/…) | Roles That Must Act
ADR-0001 | 2026-10-29 | Overall architecture (follow the reference architecture, Figure 3) | Agents & Orchestration | All | Proposed
ADR-0002 | 2026-10-29 | L13/L15 ownership split | Eval & Red-Team | L13, L15 | Proposed

## Experiments
Exp | Question | Configuration | Run Date | Task Success (n/N) | Policy Violations | Attack Success | False Blocks | Cost / Case (₹ or $) | Latency p50 (s) | Latency p95 (s) | Errors / Timeouts | Repeat # | Owner | Link
E1 | Does the agent justify its cost? | C0 fixed workflow | [10 empty] | Eval & Red-Team
E1 |  | C1 single agent | [10 empty] | Eval & Red-Team
E1 |  | C2 agent team | [10 empty] | Eval & Red-Team
E2 | Do the defences work? | Defences OFF | [10 empty] | Eval & Red-Team
E2 |  | Defences ON | [10 empty] | Eval & Red-Team
E3 | Did the lessons help? (repeat ×3) | Held-out, no playbook | [10 empty] | Eval & Red-Team
E3 |  | Held-out, with playbook | [10 empty] | Eval & Red-Team
E4 | LLM arithmetic vs calculator (₹ error) | LLM computes amounts | [10 empty] | Eval & Red-Team
E4 |  | Calculator computes amounts | [10 empty] | Eval & Red-Team
Mem | Memory on vs off | Memory OFF | [10 empty] | Knowledge & Memory
Mem |  | Memory ON | [10 empty] | Knowledge & Memory
Ret | Recall@5 before/after one change | Baseline | [10 empty] | Knowledge & Memory
Ret |  | After change | [10 empty] | Knowledge & Memory
Report every configuration, including failed and timed-out runs. Repeat the final held-out comparison 3 times and report the spread (capstone guide, p.6).